## EvaScrum Information
EvaScrum: an assessment instrument to support the diagnosis of Scrum
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co
Percentages of questions
Mandatory | 70
Complementary | 30
Answer | Abbreviation for answers
Never | N
Hardly ever | HE
Regularly | R
Always | A

## Start Phase
Start Phase | [7 empty] | Measurement units | [6 empty] | Degree of implementation of activities
Id | Activity | Question | RA: Responsible for the activity and/or PP: Performer or participant | Answer |  |  |  | vQ | gQ | gA | Ppa | Pa | vA | gF
|  |  |  | N | HE | R | A
1 | Define Scrum team. | Do you identify and choose a person who is responsible for exercising as a Product Owner? | RA: SeM/SCT PP: SeM/SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.13462 | 0.13462 | 100
|  | Do you identify and choose a person who is responsible for exercising as a Scrum Master? |  |  |  |  | x | 3 | 1
|  | Are the people responsible for exercising as development team identified and chosen? |  |  |  |  | x | 3 | 1
|  | Is the Scrum team composed of a maximum of 9 people? |  |  |  |  | x | 3 | 1
2 | Create the vision of the project. | Is there a meeting with the customer or a representative of the customer to obtain the general description of the project? | RA: SeM/SCT PP: PO |  |  |  | x | 3 | 1 | 1 | 70 | 0.13462 | 0.13462
|  | From the meeting held to obtain the general description of the project, is there an artefact containing the description generated? |  |  |  |  | x | 3 | 1
3 | Identify the requirements from the customer's point of view. | Do you use a tool or strategy to identify the requirements at a high-level of abstraction? | RA: PO PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.13462 | 0.13462
|  | Is there a meeting with the customer or a representative of the customer, where a general description of the project requirements is made? |  |  |  |  | x | 3 | 1
|  | Do the attendees at the requirements gathering meeting actively participate in that meeting? |  |  |  |  | x | 3 | 1
4 | Identify all interested (partners, sponsors, stakeholders) related to the Project. | Is an analysis carried out to determine the end users, as well as all possible interested parties and their participation in the project? | RA: SeM/SCM PP: PO |  |  |  | x | 3 | 1 | 1 | 30 | 0.057692 | 0.057692
5 | Formalize the creation of the Project through a constitutive act of the project and budget. | Is a method (record, document, mail, etc.) used to start a project? | RA: SeM/SCM PP: SeM/SCM |  |  |  | x | 3 | 1 | 1 | 70 | 0.13462 | 0.13462
|  | Is a formal document presented where the project begins? |  |  |  |  | x | 3 | 1
6 | Prioritize the elements of the wish list according to the needs of the customer. | Is the customer or a representative responsible for prioritizing the requirements according to their need? | RA: PO PP: PO |  |  |  | x | 3 | 1 | 1 | 70 | 0.13462 | 0.13462
|  | Is the wish list organized according to customer priority? |  |  |  |  | x | 3 | 1
7 | Ensure that resources are available for the proper functioning of the project. | Is it verified that there are sufficient resources (economic, personal, space) to carry out the project? | RA: SeM/SCM PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.13462 | 0.13462
|  | Do members of the scrum team have timely access to the information regarding the project? |  |  |  |  | x | 3 | 1
8 | Validation and / or re-selection of the development tool: At the moment that the vision of the Scrum team is clear and ready to begin, it is necessary to select one or several work tools that the development team considers necessary, for this reason, the development team must make clear what will be the tools they will use throughout the execution of the plan. | Is the development team clear about what work tools are going to be used in the project? | PP: SCT PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.13462 | 0.13462
|  | Does everyone involved in the project have access to established work tools? |  |  |  |  | x | 3 | 1
|  | Does everyone involved in the project know how to use the established work tools? |  |  |  |  | x | 3 | 1
Complete phase
Paper title: EvaScrum: an assessment instrument to support the diagnosis of Scrum – results of two case studies
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co

## Planning and estimation Phase
Planning and estimation Phase | [7 empty] | Measurement units | [6 empty] | Degree of implementation of activities
Id | Activity | Question | RA: Responsible for the activity and/or PP: Performer or participant | Answer |  |  |  | vQ | gQ | gA | Ppa | Pa | vA | gF
|  |  |  | N | HE | R | A
9 | Detail the customer's wishes and generate a list in the form of requirements that allow to have detailed information of what should be done in the project. | Are the requirements written at a high-level of abstraction? | RA: PO PP: PO/DevT |  |  |  | x | 3 | 1 | 1 | 70 | 0.18421 | 0.18421 | 100
|  | Do all Scrum team members have a clear understanding of the requirements? |  |  |  |  | x | 3 | 1
|  | Is the product backlog generated from the customer's requirements? |  |  |  |  | x | 3 | 1
|  | Is it verified that each requirement is sufficiently decomposed? |  |  |  |  | x | 3 | 1
10 | Define criteria that allow the Scrum team to know clearly and unanimously when an activity / task is ready or finished to be entered / updated in the sprint backlog (Definition of Ready (DoR) and Definition of Done (DoD)). | Is the ready criterion (DoR) generated? | RA: PO PP:DevT |  |  |  | x | 3 | 1 | 1 | 70 | 0.18421 | 0.18421
|  | Is it clear on the part of the team when a task is ready to be developed? |  |  |  |  | x | 3 | 1
|  | Is the done criterion (DoD) generated? |  |  |  |  | x | 3 | 1
|  | Is it clear to the team when a task is finished and ready to be integrated into the project (DoD)? |  |  |  |  | x | 3 | 1
11 | Evaluate and control the possible risks that may occur during a Sprint. | When starting a new sprint, are the risks that may arise throughout the sprint evaluated? | RA: SeM/SCT PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.18421 | 0.18421
|  | Do you have a guide, act or instrument that allows you to have a route to lessen the risks that may arise along the sprint? |  |  |  |  | x | 3 | 1
12 | Analyse the changes that are received for each Sprint in order to socialize and verify requirements and other circumstances that are affected by change requests. | Is there a meeting to analyse and socialize the changes in the project? | RA: SeM/SCT PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.18421 | 0.18421
|  | Is the estimation of the changes made and how these affect the rest of the tasks? |  |  |  |  | x | 3 | 1
|  | Is the cost and impact of changes in the project socialized to senior management or the Scrum team? |  |  |  |  | x | 3 | 1
13 | Adapt and / or refine the structure used in the project to adapt to changes that arise in the development of the plan. | If a change is necessary, is the respective adaptation made in the project? | RA: SCT PP: SCT |  |  |  | x | 3 | 1 | 1 | 30 | 0.078947 | 0.078947
14 | Define the objective of the sprint that will be carried out in such a way that it is related to the activities / tasks that will be developed in it. | Are strategies established to maximize the product increase? | RA: SCT PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.18421 | 0.18421
|  | Is a planning meeting held for each Sprint? |  |  |  |  | x | 3 | 1
|  | Does the Sprint have a duration that does not exceed 5 weeks? |  |  |  |  | x | 3 | 1
|  | When starting a sprint, is the launch schedule for the current sprint set? |  |  |  |  | x | 3 | 1
|  | Is the objective of the next sprint defined? |  |  |  |  | x | 3 | 1
|  | Are the requirements explained in such a way that they are clear to all team members? |  |  |  |  | x | 3 | 1
|  | Is it possible for all team members to understand the goal of the next sprint? |  |  |  |  | x | 3 | 1
|  | Is the ready (DoD) criterion verified for the tasks that will be included in the next sprint? |  |  |  |  | x | 3 | 1
|  | Do all Scrum team members know how long the next sprint will last? |  |  |  |  | x | 3 | 1
|  | Is the sprint backlog generated with the requirements to be developed in the next Sprint? |  |  |  |  | x | 3 | 1
Complete phase
Paper title: EvaScrum: an assessment instrument to support the diagnosis of Scrum – results of two case studies
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co

## Implementation Phase
Implementation Phase | [7 empty] | Measurement units | [6 empty] | Degree of implementation of activities
Id | Activity | Question | RA: Responsible for the activity and/or PP: Performer or participant | Answer |  |  |  | vQ | gQ | gA | Ppa | Pa | vA | gF
|  |  |  | N | HE | R | A
15 | Obtain information about the events that occur in the team to resolve any impediment that affects the normal development of the project. | Is there a daily meeting that allows to know the events of the development team? | RA: SCM PP: SCM, SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.33333 | 0.33333 | 100
|  | Does the daily meeting last a maximum of 15 minutes? |  |  |  |  | x | 3 | 1
|  | Is the team's work known for the next 24 hours? |  |  |  |  | x | 3 | 1
|  | Are you looking to solve all the problems that are exposed in the daily meeting or its equivalent? |  |  |  |  | x | 3 | 1
|  | Are the impediments recorded by the Scrum team recorded? |  |  |  |  | x | 3 | 1
16 | Develop the client's requirements. | Are designs of diagrams, databases or elements required by the project generated for each project? | RA & PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.33333 | 0.33333
|  | Does the increase take place according to customer needs? |  |  |  |  | x | 3 | 1
|  | Is documentation of the process being carried out? |  |  |  |  | x | 3 | 1
|  | Are sprint backlog elements updated? |  |  |  |  | x | 3 | 1
17 | Update the Scrum dashboard and the impediments log. | Do you have artefacts (kanban, boards, post it, etc.) or software tools (taiga, trello, etc.) that allow the team to know the status of the project? | RA: SCM PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.33333 | 0.33333
|  | Are the tools updated (Scrum board, post it, taiga, trello, etc.) that are used to know the work of the team? |  |  |  |  | x | 3 | 1
|  | Is the impairment record updated? |  |  |  |  | x | 3 | 1
Complete phase
Paper title: EvaScrum: an assessment instrument to support the diagnosis of Scrum – results of two case studies
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co

## Retrospective and review Phase
Retrospective and review Phase | [7 empty] | Measurement units | [6 empty] | Degree of implementation of activities
Id | Activity | Question | RA: Responsible for the activity and/or PP: Performer or participant | Answer |  |  |  | vQ | gQ | gA | Ppa | Pa | vA | gF
|  |  |  | N | HE | R | A
18 | Review and verify with DoD criteria the tasks that have been completed in the sprint. | Is there a review meeting to review and verify the tasks performed in the sprint? | RA: SCM PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.33333 | 0.33333 | 100
|  | Does the Sprint review meeting have a duration that does not exceed 4 hours? |  |  |  |  | x | 3 | 1
|  | At the end of a Sprint is the presentation of the tasks developed? |  |  |  |  | x | 3 | 1
|  | When a Sprint is finished, is a functional review carried out verifying the Sprint objectives? |  |  |  |  | x | 3 | 1
|  | Are the functionalities terminated in the sprint verified under the DoD criteria? |  |  |  |  | x | 3 | 1
|  | Is a list generated with the functionalities that do not meet the DoD criteria? |  |  |  |  | x | 3 | 1
|  | Are the tasks that meet the criteria for completion (DoD) integrated into the rest of the product? |  |  |  |  | x | 3 | 1
19 | Update the launch plan and the prioritized list of pending products. | When not all the tasks defined for the Sprint can be performed, is the product backlog updated with the tasks that have been pending? | RA: PO PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.33333 | 0.33333
|  | Is the product backlog prioritized with tasks that were not completed in the finished sprint? |  |  |  |  | x | 3 | 1
|  | Is a report made justifying the rejection of activities that were not approved? |  |  |  |  | x | 3 | 1
20 | Sprint Retrospective. Post-mortem analysis of what has been done, learned, obstacles, improvement actions, lessons learned, among others. | At the end of a sprint, a feedback meeting is held to collect experiences obtained by the Scrum team? | RA: SCM PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.33333 | 0.33333
|  | Are problems that affect the equipment solved? |  |  |  |  | x | 3 | 1
|  | Are facts and experiences obtained by the team documented during the sprint? |  |  |  |  | x | 3 | 1
|  | According to the facts and experiences obtained by the team during sprint, is a proposal for improvement defined? |  |  |  |  | x | 3 | 1
|  | Does the development team receive support from the Product Owner and the Scrum Master in the creation of the deliverables agreed upon for the Sprint? |  |  |  |  | x | 3 | 1
Complete phase
Paper title: EvaScrum: an assessment instrument to support the diagnosis of Scrum – results of two case studies
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co

## Closure Phase
Closure Phase | [7 empty] | Measurement units | [6 empty] | Degree of implementation of activities
Id | Activity | Question | RA: Responsible for the activity and/or PP: Performer or participant | Answer |  |  |  | vQ | gQ | gA | Ppa | Pa | vA | gF
|  |  |  | N | HE | R | A
21 | Help with the launch of the project: In this activity it is prepared what is necessary to release the final product. | Is a strategy defined (Customer training, server deployment, space adaptation, etc.) for the project launch? | RA: SCT PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.29167 | 0.29167 | 100
22 | Implementation tests: Once the product is delivered, tests must be performed in the real environment where correct operation is guaranteed. If necessary, the required changes are carried out so that the product meets all the requirements. | Are system tests performed in the environment for which it was designed? | RA: SCT PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.29167 | 0.29167
23 | Delivery of the product: At the end of the tests and to confirm that the project is ready, the formal delivery of the project to the customer is performed. | Is formal delivery of the finished product made to the customer? | RA: SeM/SCM PP: SCT |  |  |  | x | 3 | 1 | 1 | 70 | 0.29167 | 0.29167
24 | Launch meeting: At the end of the delivery, a meeting is held to obtain feedback of situations and positive and negative aspects, this is carried out, in order to establish opportunities for improvement to correct mistakes and enhance virtues. | At the end of the project process, is a feedback meeting held to discuss lessons learned? | RA: SCM PP: SCT |  |  |  | x | 3 | 1 | 1 | 30 | 0.125 | 0.125
Complete phase
Paper title: EvaScrum: an assessment instrument to support the diagnosis of Scrum – results of two case studies
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co

## Transverse Phase
Transverse Phase | [7 empty] | Measurement units | [6 empty] | Degree of implementation of activities
Id | Activity | Question | RA: Responsible for the activity and/or PP: Performer or participant | Answer |  |  |  | vQ | gQ | gA | Ppa | Pa | vA | gF
|  |  |  | N | HE | R | A
25 | Facilitate Scrum events as required or needed throughout the process. | Is there a person or group of people to whom you can go if you have any questions about the Scrum? | These activities are carried out by Scrum Master (SCM). |  |  |  | x | 3 | 1 | 1 | 70 | 0.25926 | 0.25926 | 100
|  | Is there a person or people in charge of informing about the events, activities and artefacts that Scrum proposes? |  |  |  |  | x | 3 | 1
|  | Do all Scrum team members actively participate in the events that Scrum contemplates? |  |  |  |  | x | 3 | 1
26 | Monitoring progress: The success of a project depends on the activities being carried out correctly, which is why it is necessary to verify and control the tasks and results that are being obtained throughout the entire process. | Is control of the activities carried out by the team throughout the project? |  |  |  |  | x | 3 | 1 | 1 | 70 | 0.25926 | 0.25926
|  | Is the utility and need to comply with the Scrum guidelines clear to all Scrum team members? |  |  |  |  | x | 3 | 1
27 | Help to develop the team plan with the Scrum Master. | Is there a proposed work plan? |  |  |  |  | x | 3 | 1 | 1 | 30 | 0.11111 | 0.11111
|  | Do team members and the Scrum Master contribute to the creation of the work plan? |  |  |  |  | x | 3 | 1
28 | Ensure that there is an ideal environment for the Scrum team during Sprints. | Does the team have an environment and space conducive to develop the different activities it must face? |  |  |  |  | x | 3 | 1 | 1 | 30 | 0.11111 | 0.11111
|  | Does the team manage to be motivated and deliver the maximum possible value to the customer? |  |  |  |  | x | 3 | 1
29 | Help the owner of the product in the creation of the prioritized list of outstanding products: The joint work between the client and the Scrum team must be constant, so that the client is aware of the process. In addition, it is suggested that the client be advised in the prioritization of the product backlog, ensuring the interests of both the team and the sponsors. | Does the product owner know how the product backlog should be ordered? |  |  |  |  | x | 3 | 1 | 1 | 70 | 0.25926 | 0.25926
|  | Are the elements of the product backlog constantly reviewed avoiding obsolete items? |  |  |  |  | x | 3 | 1
|  | Are you constantly interacting with the customer to agree on the delivery that best suits your needs? |  |  |  |  | x | 3 | 1
Complete phase
Paper title: EvaScrum: an assessment instrument to support the diagnosis of Scrum – results of two case studies
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co

## Overall result
| Activity | Implementation degree
| Start Phase | 100
| Planning and estimation Phase | 100
| Implementation Phase | 100
| Retrospective and review Phase | 100
| Closure Phase | 100
| Transverse Phase | 100
| Scrum implementation percentage | 100%
| Scrum implementation degree | Fully Achieved
Paper title: EvaScrum: an assessment instrument to support the diagnosis of Scrum – results of two case studies
Authors: César Jesús Pardo Calvache, Hamilton D. Jojoa, Ricardo A. Zambrano, Wilson A. Ortega Ordoñez
Universidad del Cauca, Grupo de I+D en Tecnologías de la información (GTI). Calle 5 No. 4-70, Popayán, Colombia
Email: {cpardo,wortega,hjojoa,rzambrano}@unicauca.edu.co